Vertical and horizontal distribution patterns of the bloom-forming ciliate Mesodinium rubrum

Participants

- Curtis Roegner, NOAA (chief scientist)

- 2 scientific staff, to be provided by OHSU (Michael Wilkin will identify)

Objectives:

1) Examine Mesodinium vertical migration in relation to horizontal transport

2) Determine effects of ciliate on water column parameters (DO, nutrients)

3) Compare spring and neap tidal conditions

Experiments include time series + feature tracking (Lagrangian) measurements; feature being tracked will likely be algal bloom (if present) relative to estuarine fronts or other high gradient regions.

General cruise plan

- Time series (ciliate vertical distribution with salinity & velocity)

  - near mouth to evaluate ocean dispersal

  - Near bridge to evaluate upstream transport

- Track bloom patch, measuring xyz position & water column attributes

  - Model comparison?

  - Drifters (available?).  *** probably not for August; a consideration for future cruises ***

  - Algal distribution and frontal features

Measurements:

- Vessel position

- CTD (S, T, D, DO, Chl).

  - Every ½ h.

- Water samples (Niskin bottles)

  - Standard nutrient suite.

    - Every 1.5 h

    - Vertical: 1 m , pycnocline, 1m > bottom, Chl max

  - algal species sample (unfiltered samples)

    - from Chl max

Schedule:

NEAP SERIES (High-tide to high-tide)

- 21 August, anchor station (AS) near Mouth

- 22 August, feature tracking (FT)

- 23 August AS near Bridge

- SPRING SERIES (low-tide to low-tide)

- 28 August, AS near Mouth

- 29 August, FT

- 30 August AS near Bridge

* North or South channel, depending on Barnes/Wecoma location, but prefer North channel .