APPENDIX 2

## CRUISE PLAN R/V WECOMA

Oregon State University

College of Oceanic & Atmospheric Sciences

| FILING DATE: | 01 May 2008 |
| --- | --- |
| CRUISE NUMBER: |  |
| TITLE: | Science and Technology Center for Coastal Margin Observation and Prediction (CMOP) |
| CONTRACT/GRANT NUMBER: | NSF |
| PRINCIPAL INVESTIGATOR(S): | Antonio M. Baptista et al. |

PURPOSE: (Short, non-technical statement on how cruise relates to overall project)

The goals of R/V Wecoma operations are: - Occupy a grid of stations over the Oregon and Washington continental shelf and slope to measure hydrographic (T, S, pressure), bio-optical (chlorophyll fluorescence, light transmission) and chemical (nitrate, dissolved oxygen) parameters. Combine these data with ADCP measurements of subsurface velocity to explore biophysical interactions. - Collect water samples for membrane lipid and DNA- and RNA-based microbial community analyses, primary and secondary production rates and water chemistry studies across environmental gradients in pelagic environments of the Columbia River estuary, the Columbia River plume, the Columbia River at Beaver Army Dock and along established sampling lines along the Oregon and Washington coasts. - Collect surface sediments in Columbia River, estuary, plume and at a few sites on coastal lines using a multicorer. - Make continuous measurements of surface water chemistry with several devices attached to the continuous flow seawater system. - Feature Tracking exercise using the SWAP system and model-based now-cast/forecast system to follow the Columbia River Plume.

ITINERARY: (Include station positions and route waypoints. Please send/fax/or bring a PAGE SIZE CRUISE TRACK for submission to UNOLS).

Please see attached

| # WILL RADIOACTIVE METHODS BE USED? | X | YES |  | NO |
| --- | --- | --- | --- | --- |
| If so, list OSU radiation use authorization number: Applied For |  |  |  |  |

| # WILL YOU BE BRINGING HAZARDOUS MATERIALS ABOARD? | X | YES |  | NO |
| --- | --- | --- | --- | --- |
| If so, you are responsible for providing the Master with an Inventory of such materials & associated MSDS sheets. |  |  |  |  |

SAMPLING PLAN:

We will perform CTD casts with and without water collection using the rosette of the Wecoma. At selected sites we will collect sediments using a multicorer depending on the kind of sediment found at a given site.

| EQUIPMENT REQUIRED: (Should be included on Shared-Use Equipment request form) |  |
| --- | --- |
| Equipment List /R/V Wecoma /for/ /June cruise (28 May - 7 June 2008) Standard Ship’s Outfit a. SeaBird CTD system with transmissometer, fluorometer, PAR, O2, altimeter. b. SBE Carousel samplers - 12 bottles. 10L bottles c. RDInstruments shipboard Doppler current profilers; Frequency 75/300 kHz. Dual system required. d. DAS shipboard data logging/display system e. Shipboard networking services f. Winch slip rings - 4-conductor – for CTD g. Dry Lab tables and cabinets in various heights and sizes h. Portable refrigerator (15 cu. ft.) i. Portable chest freezers (2 freezers required, each 7 ft3 ) Transient Equipment j. Low Temperature freezer (1 available) -85 oC, 5 cu. ft. Ship’s Deck Equipment l. Hydro Winch: 0.322” 3-conductor EM for CTD, 1000m max depth. m. Hydro A-Frame for deploying CTD and Niskin Bottles n. Gifford block mounted on A-frame o. Coring Winch: 3/8" wire from the trawl winch for deploying multi corer. 1000m max depth Vans t. Storage Van u. New Radiation Laboratory Van |  |
| SCIENTIFIC PERSONNEL TO BE ONBOARD: (Provide full legal name & affiliation) |  |
| Scientist in Charge: | Tawnya Peterson (OHSU) |
| Other Scientist(s): | Carme Huguet (UW), Mariya Smit (OHSU) |
| Party Chief: |  |
| Technicians: | Mikaela Selby (OHSU), Paul Walczak (OSU), Melissa Rohde (OHSU) |
| Grad Students: | Wiley Evans (OSU), Michael Malpezzi (UMCES) |
| Undergraduate Students: |  |
| Observers: | Elise Engler (artist) |

| OSU Marine Technician(s) Assigned to Cruise: | David O’ Gorman |
| --- | --- |

| USER SUPPLIED EQUIPMENT: |  |
| --- | --- |
| Vans/Containers: |  |
| Number: |  |
| Size: |  |
| Estimated Weight: |  |
| Location: |  |

| OTHER BULKY HEAVY ITEMS: |  |
| --- | --- |
| Location: |  |
| Estimated Weight: |  |

| BILLING INFORMATION: |  |
| --- | --- |
| Name: |  |
| Address: |  |
| City, State, Zip |  |
| Phone: |  |
| Account Number (or number to reference): |  |

| # DO YOU WANT CELLULAR/INMARSAT PHONE ACCESS: | X | YES |  | NO |
| --- | --- | --- | --- | --- |
| Chief Scientist will be responsible for all charges – dedicated science phone. |  |  |  |  |

CMOP cruise plan

Oregon & Washington Coasts and Columbia River, Plume & Estuary

R/V Wecoma

May 28 – June 7, 2008

Area of Operations: Pacific Northwest coastal ocean from South Oregon to North Washington, Columbia River plume, Columbia River and its estuary

Scientific personnel

| Name | Inst | Activity | Berth | Watch | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tawnya Peterson | OHSU | Chief Scientist | S15 | D | X | X | X | X | X | X | X | X | X | X | X |
| Mikaela Selby | OHSU | Water, filter | S2 | D | X | X | X | X | X | X | X | X | X | X | X |
| Carme Huguet | UW | Water/sediment | S6 | D | X | X | X | X | X | X | X | X | X | X | X |
| Mariya Smit | OHSU | Water; filter | S7 | D | X | X | X | X | X | X | X | X | X | X | X |
| Melissa Rohde | OHSU | water | S1 | D | X | X | X | X | X | X | X | X | X | X | X |
| Wiley Evans | OSU | CTD/pCO2 | S3 | D | X | X | X | X | X | X | X | X | X | X | X |
| Michael Malpezzi | UMCES | Water; BP | S4 | D | X | X | X | X | X | X | X | X | X | X | X |
| Elise Engler |  | Artist | S8 | D | X | X | X | X | X | X | X | X | X | X | X |
| Paul Walczak | OSU | sediments | S18 | D | X | X | X | X | X | X | X | X | X | X | X |
| Dave O’Gorman | OSU | Mar tech | 18 | D | X | X | X | X | X | X | X | X | X | X | X |

Watches: No watches will be assigned to science crew due to lack of night operations.

R/V Wecoma objectives and operations

The goals of R/V Wecoma operations are to:

- Occupy a grid of stations over the Oregon and Washington continental shelf and slope to measure hydrographic (T, S, pressure), bio-optical (chlorophyll fluorescence, light transmission) and chemical (nitrate, dissolved oxygen) parameters. Combine these data with ADCP measurements of subsurface velocity to explore biophysical interactions.

- Collect water samples for membrane lipid and DNA- and RNA-based microbial community analyses, bacterial and primary production rates and water chemistry studies across environmental gradients in pelagic environments of the Columbia River estuary, the Columbia River plume, the Columbia River at Beaver Army Dock and along established sampling lines along the Oregon and Washington coasts. We will carry incubations on deck.

- Collect surface sediments in Columbia River, estuary, plume and at a few sites on coastal lines using a multicore, boxcorer and grab sampler.

- Make continuous measurements of surface water chemistry with several devices attached to the continuous flow seawater system.

- Feature Tracking exercise using the SWAP system and model-based now-cast/forecast system to follow the Columbia River Plume.

We kindly request copies of all calibration/information sheets for R/V Wecoma instruments.

Activities

I. CTD deployment

  - David O’ Gorman

  - Tawnya Peterson

  - Wiley Evans

II. Water sample processing

- Filling up bottles from CTD for biology team (Rohde, Peterson)

- Dissolved and particulate chemistry (nutrients and organic matter) (Smit, Malpezzi)

  - Nitrate plus nitrite, nitrite, ammonium, phosphate, silicic acid

  - Dissolved organic carbon/nitrogen

  - Total suspended solids

  - Particulate organic carbon/nitrogen

  - Fixed samples

- Chlorophyll and other phytoplankton pigments (Rhode/Peterson)

- DNA and RNA samples  (Selby)

- Bacterial Production measurements in radioisotope van (Malpezzi)

- Primary production (Peterson/Rohde)

- Water filtration for membrane lipid samples (Huguet)

III. Feature Tracking

Using SWAP system to track and follow Columbia River Plume (Smit, Peterson)

IV. Sediment

- Paul Walczak (coring operations)

- Carme Huguet (processing sediment cores)

V. Mapping

Mapping using the ship’s flow-through system will be conducted at night. Ship’s tracks will be selected to capture features of interest to surface ocean biogeochemistry (Evans, Peterson, and all interested parties).

Cruise Plan Summary

Dates / Location / CTDs # / Maximum # of water samples for biology team / Coring site #

| Date | Location† | # CTDs | Microbial process stns* | Coring+ |
| --- | --- | --- | --- | --- |
| 05/28/08 | NH line - offshore | 2 | 1 | 0 |
| 05/29/08 | NH line | 10 | 4 | 1 |
| 05/30/08 | NH line + alongshore transect | 5 | 5 | 0 |
| 05/31/08 | Plume study – neap | ~10 | 4 | 0 |
| 06/01/08 | CR line | 8 | 4 | 2 |
| 06/02/08 | Estuary – south channel | 8 | 6 | 3 |
| 06/02/08 | Estuary – north channel | 3 | 0 | 0 |
| 06/03/08 | Beaver Army dock | 4 | 2 | 1 |
| 06/03/08 | Plume study - spring | ~10 | 2 | 0 |
| 06/04/08 | LP line | 7 | 3 | 1 |
| 06/05/08 | GH line | 8 | 0 | 1 |
| 06/06/08 | NH-10 survey | 11 | 0 | 0 |
| 06/07/08 | dock | 0 | 0 | 0 |
|  | Total | 86 | 31 | 9 |

†Station locations can be found in the Appendix

*Microbial process stations will typically collect water at 3-6 depths

+If time allows, additional coring will be done at NH-3 (48m) and LP-6 (55).

Cruise Plan Details

27 May 2008

08:00		Load ship in Newport (44.63N, 124.04W). Load radiation van and coring equipment on main deck (multicorer, extruder)

28 May 2008

08:00 		Departure for NH-10 (shakedown station; one CTD cast with water samples at 3 depths)

09:00 – 10:00 	Safety meeting

10:15 – 12:15	NH-10(w) (see Table 1a for station locations)

12:15		Depart for NH-55 (see Table 1a for Way Points)

18:15		Arrive at NH-55(w) (two CTD casts for microbiology team)

21:30		End NH-55

21:30		Begin night mapping (see Table 2a for Way Points)

21:35 – 07:00	Night mapping along NH line, from NH-55 to NH-10 and back to NH-55

29 May 2008

07:00		Arrive at NH-55

07:15		Productivity cast NH-55 (profile, 4-6 depths shallower than 60 m)

08:00		Steam to NH-45; deploy CTD at NH-45, 35, 25, 20(w), 15, 10(w), 5(w), 3, 1. Sediment coring at NH-10. See Table 1b for station locations.

23:15		Finish NH line; begin night mapping (NH-1 toward Siletz Bay and back; see Table 2b for Way Points)

30 May 2008

07:30		Arrive at NH-1

07:40		NH-1(w), productivity cast (PP)

08:30		Steam to alongshore stations at Siletz Bay(w), Nestucca River(w), Tillamook Bay(w), Nehalem River(w) (see Table 1c for station locations). Surface water only for microbiology; 3 depths for pigments and nutrients.

22:30		Steam to Night Mapping Way Points (Table 2c). Night mapping survey off Seaside, OR to capture potential cyclonic recirculation feature south of CR mouth.

31 May 2008: Plume study Neap

07:00		Plume stations, P1 – P15 (see Table 1d for locations); exact locations to be determined from CORIE forecast. Water to be collected at 4 stations (3 depths) in fresh and aged plume.

20:10		End Plume survey, transit to CR-4 (see Table 2d for Mapping Way Points).

01 June 2008: CR line

06:30	Begin Columbia River line transect: CTD at 8 stations in the following order: CR-4, CR-7(w), CR-10, CR-15(w), CR-20, CR-25, CR-30(w), CR-40(w); 3 depths for each (microbiology and lipids at all 4 water sites, primary production at CR-7). Coring at CR-7 and CR-15 (55 & 110 m depth, respectively). (see Table 1e for station locations).

21:55	Begin night mapping (see Table 2e for Way Points). Travel from CR-40 to CR-7, and steam to RM-1, RM-4, RM-8, and NC-11.

02 June 2008: Estuary – South and North Channels

06:00	Arrive at NC-11 (low tide at 06:48); transit between NC-11 and NC-7 for 1 h, then transit to the South Channel of the Columbia River estuary at site with salinity of 15 PSU (exact location will be determined the previous day using the CORIE forecast).

09:45	During slack tide (09:45 & 15:30); high tide at 13:29 & low at 06:48 and 18:26) sample a salinity gradient aiming to get salinity: 0, 5, 10, 15, 20 and 25 PSU. More than 6 CTDs may need to be done to find the correct salinity values. Start with salinity of 15 PSU. (microbiology at all 6 water sites, primary production at 15 PSU, lipids at 0, 5, 15 & 20 PSU). Coring at 3 sites: 0, 15 and 20 PSU (10-20 m depth). See Table 1f for potential station locations.

17:30	Travel to NC-11 and stay on station over night in Estuary North Channel at station NC-11 and during slack tide (high tide ~01:48); deploy CTDs at 21:45, 22:30, 23:15. This is to compare data with Saturn-01. See Table 2f for latitude/longitude.

23:15	End

03 June 2008: River (Beaver Army Dock; Plume Study Spring)

03:00	Begin transit to Beaver Army dock (departure time can be adapted as necessary to be at Beaver Army Dock at 06:30)

06:30	Begin sampling at station Beaver Army Dock: 4 CTDs at 06:30, 07:00, 7:30 and 08:00 with Niskin bottles sampling surface water at 07:00 and 08:00 (microbiology at 07:00 and 08:00, primary production  and lipids at 07:00). Coring at Beaver Army dock after the last CTD.

08:30	Transit to Columbia River Plume (exact coordinate will be provided by the CORIE forecast on June 01).

12:00	Start feature tracking (CTDs at pre-determined sites and times). Do ~9 CTDs (exact number will depend on transit time from Beaver Army dock to Plume); water collection at 2 sites characterized by a range of surface water salinities within the plume, with 3 depths for each (microbiology and lipids at both water sites). See Table 1g for station locations (day) and Table 2g for Way Points (night).

21:00	End

04 June 2008: LP line

08:15	Begin LaPush line transect: CTD at 7 stations in the following order: LP-4, LP-6(w), LP-17(w), LP-22, LP-27, LP-32 and LP-52(w); with 3 depths for each (microbiology at all 3 water sites, primary production at LP-6, lipids at LP-6 & LP-17). Coring at LP-6 (55 m depth). See Table 1h for station locations (day) and Table 2h for Way Points (night).

23:00	End

05 June 2008: GH line

08:45	Begin Grays Harbor line transect from GH-1 to GH-41 (pigments and nutrients only, no microbiology): GH-1, GH-2, GH-3(w), GH-6, GH-10, GH-21(W), GH-26, GH-31, GH-36, GH-41(W). See Table 1i for station locations.

18:52	End; begin steaming toward NH-10 (See Table 2i for Way Points).

06 June 2008: NH-10 survey

09:00	Arrive at NH-10. Do a 12-h survey around NH-10 (see Table 1j for station locations); collect water for nutrients and pigments, no microbiology.

22:30	End NH-10 CTD survey, but continue steaming around NH-10 mooring (see Table 2j for Way Points).

07 June 2008: dock

06:00	Finish NH-10 survey, head for Newport.

07:30	Dock at Newport and unload ship.

Notes

-Surface is defined for all as 2 m from surface

-Bottom is defined in plume and coastal lines as 5 m from bottom

-Bottom is defined in estuary (salinity gradient) and station Beaver Army Dock as 1 m from bottom

-Location of stations for estuary (June 2) and plume work (May 31, June 3) will be determined the day before based on CORIE forecast.

-(w) indicates water to be collected from Niskins; bold & underline indicates microbiology cast

Station Tables for CTD casts & night mapping Way Points

Table 1a. May 28 (Newport Line). Assuming a 08:00 departure, plan for ‘shakedown station’ at ~10:00, NH-55 at approximately 21:30.

Table 1b. May 29 (Newport Line). Start at 07:15, end at ~23:15.

Table 1c. May 30 (Coastal Rivers). Start at 07:30, end at ~22:30.

Table 1d. May 31. Plume study, example stations; exact locations to be determined from CORIE forecast. End ~21:00.

Table 1e. June 1, CR-line.

Table 1f. June 2, Estuary sampling.

Table 1g. June 3, Beaver Army Dock and plume stations (feature tracking). Exact coordinates for the latter will be provided by CORIE forecast.

Table 1h, June 4. La Push line.

Table 1i, June 5. Grays Harbor line.

Table 1j, June 6. NH-10 horizontal variability sampling.

Appendix 2. Night mapping Way Points

Table 2a. May 28-29. After finishing microbial work at NH-55, steam toward NH-5 (to 124.25oW) and back to NH-55. NH line will begin at ~07:15 on May 29.

Table 2b. May 29-30. Alongshore survey from NH-1 to Siletz Bay.

Table 2c. Night survey, May 30-May 31. Line off Seaside, OR just south of Columbia River mouth.

Table 2d. Night survey, May 31-June 1. Plume survey.

Table 2e. Night survey, CR-line and Astoria Bridge (NC-11).

Table 2f. Estuary sampling, night (June 2-3, 2008).

Table 2g. Travel from plume to La Push line (June 3-4).

Table 2h. Travel from La Push to Grays Harbor line (June 4).

Table 2i. Travel from GH-46 to NH-10 (June 5-6).

Table 2j. Night survey around NH-10 (June 6-7).